## Sheet1
Upper Coastal Plain RPO 5 year Planning Program and Calendar Time Line
July 1, 2008 to June 30, 2013
PWP Work Item
II-A | Surveillance of Inventory Data:
II-A-2 |  | Status of Transportation Plans
2008-2009 | Inventory and status of transportation plans along with a list of potential studies for DOT’s consideration for FY 2009-10
2009-2010 | Inventory and status of transportation plans along with a list of potential studies for DOT’s consideration for FY 2010-11
2010-2011 | Inventory and status of transportation plans along with a list of potential studies for DOT’s consideration for FY 2011-12
2011-2012 | Inventory and status of transportation plans along with a list of potential studies for DOT’s consideration for FY 2012-13
2012-2013 | Inventory and status of transportation plans along with a list of potential studies for DOT’s consideration for FY 2013-14
II-A-5 |  | Transit System Data
2008-2009 | Inventory of UCP RPO area Transit services and route information as well as any other information necessary for plan development
2009-2010 | N/A
2010-2011 | Maintenance of data collected in FY 2008-2009
2011-2012 | N/A
2012-2013 | Maintenance of data collected in FY 2010-2011
II-A-9 |  | Mapping / Data Inventory
2008-2009 | A listing or database of available maps and data for use by the RPO and a list of items needed for future evaluation of the RPO
2009-2010 | A listing or database of available maps and data for use by the RPO and a list of items needed for future evaluation of the RPO
2010-2011 | A listing or database of available maps and data for use by the RPO and a list of items needed for future evaluation of the RPO
2011-2012 | A listing or database of available maps and data for use by the RPO and a list of items needed for future evaluation of the RPO
2012-2013 | A listing or database of available maps and data for use by the RPO and a list of items needed for future evaluation of the RPO
II-B | Long Range Transportation Plan:
II-B-1 |  | Collection of Data
2008-2009 | GIS data collection as well as CTP plan coordination; CTP needs for the RPO
2009-2010 | GIS data maintenance as well as CTP plan coordination; CTP needs for the RPO
2010-2011 | GIS data maintenance as well as CTP plan coordination; CTP needs for the RPO
2011-2012 | GIS data maintenance as well as CTP plan coordination; CTP needs for the RPO
2012-2013 | GIS data maintenance as well as CTP plan coordination; CTP needs for the RPO
II-B-2 |  | Collection of Network Data
2008-2009 | Collection of network data for the development of the Wilson County CTP
2009-2010 | Continued collection of network data for the development of the Wilson County CTP
2010-2011 | N/A
2011-2012 | N/A
2012-2013 | N/A
II-B-3 |  | Travel Surveys
2008-2009 | Development, disbursement, and compilation of travel surveys for Wilson CTP
2009-2010 | N/A
2010-2011 | N/A
2011-2012 | N/A
2012-2013 | N/A
II-B-8 |  | Highway Element of the LRTP
2008-2009 | Coordination with NCDOT to evaluate projected travel, safety, and other elements prudent to the development of the Wilson Co. CTP
2009-2010 | Coordination with NCDOT to evaluate projected travel, safety, and other elements prudent to the development of the Wilson Co. CTP
2010-2011 | N/A
2011-2012 | N/A
2012-2013 | N/A
II-B-10 |  | Bicycle & Pedestrian Element of the LRTP
2008-2009 | Update inventory of existing and proposed Bicycle and Ped elements for Wilson Co. CTP
2009-2010 | Update inventory of existing and proposed Bicycle and Ped elements for Wilson Co. CTP
2010-2011 | N/A
2011-2012 | N/A
2012-2013 | N/A
II-B-17 |  | Air Quality Planning / Conformity Analysis
2008-2009 | Inform member governments of CMAQ funding and work with member governments to apply for CMAQ funds
2009-2010 | Inform member governments of CMAQ funding and work with member governments to apply for CMAQ funds
2010-2011 | Inform member governments of CMAQ funding and work with member governments to apply for CMAQ funds
2011-2012 | Inform member governments of CMAQ funding and work with member governments to apply for CMAQ funds
2012-2013 | Inform member governments of CMAQ funding and work with member governments to apply for CMAQ funds
III-A | Planning Work Program
2008-2009 | Update FY 09-10 Planning Work Program (PWP) for RPO including budget and five-year calendar
2009-2010 | Update FY 10-11 Planning Work Program (PWP) for RPO including budget and five-year calendar
2010-2011 | Update FY 11-12 Planning Work Program (PWP) for RPO including budget and five-year calendar
2011-2012 | Update FY 12-13 Planning Work Program (PWP) for RPO including budget and five-year calendar
2012-2013 | Update FY 13-14 Planning Work Program (PWP) for RPO including budget and five-year calendar
III-B | Transportation Improvement Program
2008-2009 | Submit TIP Priority List for 2011-2017 TIP, Update priority rating system
2009-2010 | Develop TIP prioritization system for UCPRPO; Prepare comments on Draft 2011-2017 TIP
2010-2011 | Submit TIP Priority List for 2013-2019 TIP
2011-2012 | Prepare comments on Draft 2013-2019 TIP
2012-2013 | Submit TIP Priority List for 2015-2021
III-C | Civil Rights Compliance (Title VI) and Other Regulatory Requirements
III-C-2 |  | Environmental Justice
2008-2009 | Provide public involvement geared toward minority or low-income areas
2009-2010 | Provide public involvement geared toward minority or low-income areas
2010-2011 | Provide public involvement geared toward minority or low-income areas
2011-2012 | Provide public involvement geared toward minority or low-income areas
2012-2013 | Provide public involvement geared toward minority or low-income areas
III-C-7 |  | Public Involvement
2008-2009 | Update Appendix to Public Participation Plan and Orientation to RPO Materials
2009-2010 | Update Appendix to Public Participation Plan and Orientation to RPO Materials
2010-2011 | Update Appendix to Public Participation Plan and Orientation to RPO Materials
2011-2012 | Update Appendix to Public Participation Plan and Orientation to RPO Materials
2012-2013 | Update Appendix to Public Participation Plan and Orientation to RPO Materials
III-D | Incidental Planning & Project Development
III-D-3 |  | Special Studies
2008-2009 | Provide an evaluation of special studies for future PWPs; as well as studies and plans as required
2009-2010 | The deliverables for this line item will vary depending on the project that is approved by the TAC
2010-2011 | The deliverables for this line item will vary depending on the project that is approved by the TAC
2011-2012 | The deliverables for this line item will vary depending on the project that is approved by the TAC
2012-2013 | The deliverables for this line item will vary depending on the project that is approved by the TAC
III-D-4 |  | Regional or Statewide Planning
2008-2009 | Involvement in Regional and Statewide Planning projects including updates of RPO website
2009-2010 | Involvement in Regional and Statewide Planning projects including updates of RPO website
2010-2011 | Involvement in Regional and Statewide Planning projects including updates of RPO website
2011-2012 | Involvement in Regional and Statewide Planning projects including updates of RPO website
2012-2013 | Involvement in Regional and Statewide Planning projects including updates of RPO website
III-E | Administration & Services
2008-2009 | Conduct TCC/TAC meetings as well as create and submit quarterly/annual progress reports, as well as other admin documentation
2009-2010 | Conduct TCC/TAC meetings as well as create and submit quarterly/annual progress reports, as well as other admin documentation
2010-2011 | Conduct TCC/TAC meetings as well as create and submit quarterly/annual progress reports, as well as other admin documentation
2011-2012 | Conduct TCC/TAC meetings as well as create and submit quarterly/annual progress reports, as well as other admin documentation
2012-2013 | Conduct TCC/TAC meetings as well as create and submit quarterly/annual progress reports, as well as other admin documentation
**General assessment of line items will be done each fiscal year during Planning Work Program preparation to determine
whether or not items should be included into the following year PWP or into Five Year Calendar
The Upper Coastal Plain RPO Rural Transportation Advisory Committee (RTAC) approved the RPO Five (5) Year Planning Program
and Calendar Timeline for the Upper Coastal Plain Rural Transportation Planning Organization (RPO)
on the 11th day of March 2009.
Troy Lewis, Chair, Upper Coastal Plain RPO TCC |  |  | A.P. Coleman, Chair, Upper Coastal Plain RPO TAC
Daniel N. Van Liere, Secretary Upper Coastal Plain RPO TCC |  |  | Daniel N. Van Liere, Secretary Upper Coastal Plain RPO TAC