## Sheet1
Upper Coastal Plain RPO 5 year Planning Program and Calendar Time Line
July 1, 2009 to June 30, 2014
PWP Work Item
II-A | Surveillance of Inventory Data:
II-A-2 |  | Status of Transportation Plans
2009-2010 | Inventory and status of transportation plans along with a list of potential studies for DOT’s consideration for FY 2010-11
2010-2011 | Inventory and status of transportation plans along with a list of potential studies for DOT’s consideration for FY 2011-12
2011-2012 | Inventory and status of transportation plans along with a list of potential studies for DOT’s consideration for FY 2012-13
2012-2013 | Inventory and status of transportation plans along with a list of potential studies for DOT’s consideration for FY 2013-14
2013-2014 | Inventory and status of transportation plans along with a list of potential studies for DOT’s consideration for FY 2014-15
II-A-3 |  | Street System Inventory
2009-2010 | Develop data interoperability tool to standardize and create statewide centerline file for UCP RPO utilization
2010-2011 | N/A
2011-2012 | Maintenance of data collected in FY 2009-2010
2012-2013 | N/A
2013-2014 | Maintenance of data collected in FY 2011-2012
II-A-4 |  | Traffic Accidents
2009-2010 | Collect traffic accident data for development of the Johnston, Nash, and Wilson County CTP.
2010-2011 | N/A
2011-2012 | Collect traffic accident data as requested by member governments
2012-2013 | N/A
2013-2014 | Collect traffic accident data as requested by member governments
II-A-6 |  | Dwelling Unit, Pop., & Employment Changes
2009-2010 | Inventory of UCP RPO area Transit services and route information as well as any other information necessary for plan development
2010-2011 | N/A
2011-2012 | Maintenance of data collected in FY 2009-2010
2012-2013 | N/A
2013-2014 | Maintenance of data collected in FY 2011-2012
II-A-9 |  | Mapping / Data Inventory
2009-2010 | A listing or database of available maps and data for use by the RPO and a list of items needed for future evaluation of the RPO
2010-2011 | A listing or database of available maps and data for use by the RPO and a list of items needed for future evaluation of the RPO
2011-2012 | A listing or database of available maps and data for use by the RPO and a list of items needed for future evaluation of the RPO
2012-2013 | A listing or database of available maps and data for use by the RPO and a list of items needed for future evaluation of the RPO
2013-2014 | A listing or database of available maps and data for use by the RPO and a list of items needed for future evaluation of the RPO
II-B | Long Range Transportation Plan (LRTP):
II-B-1 |  | Collection of Data
2009-2010 | GIS data collection as well as CTP plan coordination; CTP needs for the RPO
2010-2011 | GIS data maintenance as well as CTP plan coordination; CTP needs for the RPO
2011-2012 | GIS data maintenance as well as CTP plan coordination; CTP needs for the RPO
2012-2013 | GIS data maintenance as well as CTP plan coordination; CTP needs for the RPO
2013-2014 | GIS data maintenance as well as CTP plan coordination; CTP needs for the RPO
II-B-2 |  | Collection of Network Data
2009-2010 | Working to develop data operability tool for centerline data to be utilized during Johnston, Nash, and Wilson Co. CTP development
2010-2011 | Continued collection of network data for the development of the Johnston, Nash, and Wilson Co. CTP
2011-2012 | N/A
2012-2013 | N/A
2013-2014 | N/A
II-B-5 |  | Community Goals and Objectives
2009-2010 | Development, disbursement, and compilation of travel surveys for Johnston, Nash, and Wilson CTP
2010-2011 | N/A
2011-2012 | N/A
2012-2013 | N/A
2013-2014 | N/A
II-B-7 |  | Capacity Deficiency Analysis
2009-2010 | Coordination with NCDOT to develop capacity deficiency maps as part of Johnston, Nash, and Wilson Co. CTP
2010-2011 | Coordination with NCDOT to develop capacity deficiency maps as part of Johnston, Nash, and Wilson Co. CTP
2011-2012 | N/A
2012-2013 | N/A
2013-2014 | N/A
II-B-10 |  | Bicycle & Pedestrian Element of the LRTP
2009-2010 | Coordinate with NCDOT to study Bike & Ped infrastructure in Johnston, Nash, and Wilson Co. for CTP development
2010-2011 | Coordinate with NCDOT to study Bike & Ped infrastructure in Johnston, Nash, and Wilson Co. for CTP development
2011-2012 | N/A
2012-2013 | N/A
2013-2014 | N/A
II-B-17 |  | Air Quality Planning / Conformity Analysis
2009-2010 | Inform member governments of CMAQ funding and work with member governments to apply for CMAQ funds
2010-2011 | Inform member governments of CMAQ funding and work with member governments to apply for CMAQ funds
2011-2012 | Inform member governments of CMAQ funding and work with member governments to apply for CMAQ funds
2012-2013 | Inform member governments of CMAQ funding and work with member governments to apply for CMAQ funds
2013-2014 | Inform member governments of CMAQ funding and work with member governments to apply for CMAQ funds
III-A | Planning Work Program
2009-2010 | Update FY 10-11 Planning Work Program (PWP) for RPO including budget and five-year calendar
2010-2011 | Update FY 11-12 Planning Work Program (PWP) for RPO including budget and five-year calendar
2011-2012 | Update FY 12-13 Planning Work Program (PWP) for RPO including budget and five-year calendar
2012-2013 | Update FY 13-14 Planning Work Program (PWP) for RPO including budget and five-year calendar
2013-2014 | Update FY 14-15 Planning Work Program (PWP) for RPO including budget and five-year calendar
III-B | Transportation Improvement Program
2009-2010 | Develop TIP prioritization system for UCPRPO; Prepare comments on Draft 2011-2017 TIP
2010-2011 | Submit TIP Priority List for 2013-2019 TIP
2011-2012 | Prepare comments on Draft 2013-2019 TIP
2012-2013 | Submit TIP Priority List for 2015-2021
2013-2014 | Prepare comments on Draft 2015-2021 TIP
III-C | Civil Rights Compliance (Title VI) and Other Regulatory Requirements
III-C-1 |  | Title VI
2009-2010 | Provide public involvement geared toward minority or low-income areas
2010-2011 | Provide public involvement geared toward minority or low-income areas
2011-2012 | Provide public involvement geared toward minority or low-income areas
2012-2013 | Provide public involvement geared toward minority or low-income areas
2013-2014 | Provide public involvement geared toward minority or low-income areas
III-C-2 |  | Environmental Justice
2009-2010 | Provide public notices, plans and other information regarding Johnston, Nash, and Wilson Co. CTP in other languages as necessary
2010-2011 | Provide public notices, plans and other information regarding Johnston, Nash, and Wilson Co. CTP in other languages as necessary
2011-2012 | Provide public notices, plans and other information in other languages as necessary
2012-2013 | Provide public notices, plans and other information in other languages as necessary
2013-2014 | Provide public notices, plans and other information in other languages as necessary
III-C-7 |  | Public Involvement
2009-2010 | Update Appendix to Public Participation Plan and Orientation to RPO Materials
2010-2011 | Update Appendix to Public Participation Plan and Orientation to RPO Materials
2011-2012 | Update Appendix to Public Participation Plan and Orientation to RPO Materials
2012-2013 | Update Appendix to Public Participation Plan and Orientation to RPO Materials
2013-2014 | Update Appendix to Public Participation Plan and Orientation to RPO Materials
III-D | Incidental Planning & Project Development
III-D-3 |  | Special Studies
2009-2010 | Develop regional intersection/interchange inventory for economic development purposed within UCPRPO area
2010-2011 | Continue develop of regional intersection/interchange inventory for economic development purposed within UCPRPO area
2011-2012 | Continue develop of regional intersection/interchange inventory for economic development purposed within UCPRPO area
2012-2013 | Continue develop of regional intersection/interchange inventory for economic development purposed within UCPRPO area
2013-2014 | Continue develop of regional intersection/interchange inventory for economic development purposed within UCPRPO area
III-D-4 |  | Regional or Statewide Planning
2009-2010 | Involvement in Regional and Statewide Planning projects including updates of RPO website
2010-2011 | Involvement in Regional and Statewide Planning projects including updates of RPO website
2011-2012 | Involvement in Regional and Statewide Planning projects including updates of RPO website
2012-2013 | Involvement in Regional and Statewide Planning projects including updates of RPO website
2013-2014 | Involvement in Regional and Statewide Planning projects including updates of RPO website
III-E | Administration & Services
2008-2009 | Conduct TCC/TAC meetings as well as create and submit quarterly/annual progress reports, as well as other admin documentation
2009-2010 | Conduct TCC/TAC meetings as well as create and submit quarterly/annual progress reports, as well as other admin documentation
2010-2011 | Conduct TCC/TAC meetings as well as create and submit quarterly/annual progress reports, as well as other admin documentation
2011-2012 | Conduct TCC/TAC meetings as well as create and submit quarterly/annual progress reports, as well as other admin documentation
2012-2013 | Conduct TCC/TAC meetings as well as create and submit quarterly/annual progress reports, as well as other admin documentation
**General assessment of line items will be done each fiscal year during Planning Work Program preparation to determine
whether or not items should be included into the following year PWP or into Five Year Calendar
The Upper Coastal Plain RPO Rural Transportation Advisory Committee (RTAC) approved the RPO Five (5) Year Planning Program
and Calendar Timeline for the Upper Coastal Plain Rural Transportation Planning Organization (RPO)
on the 11th day of March 2009.
Troy Lewis, Chair, Upper Coastal Plain RPO TCC |  |  | A.P. Coleman, Chair, Upper Coastal Plain RPO TAC
Daniel N. Van Liere, Secretary Upper Coastal Plain RPO TCC |  |  | Daniel N. Van Liere, Secretary Upper Coastal Plain RPO TAC